## Loan_Terms
field | value
projectName | Potwine Passive House
borrowerName | Potwine Builders LLC
loanType | residential
loanAmount | 850000
totalBudget | 1050000
currency | USD
retainagePct | 10
retainageStepDownAt | 50
retainageStepDownTo | 5
coThresholdSingle | 50000
coThresholdCumulativePct | 5
materialDelayDays | 60
cureDaysMonetary | 10
cureDaysNonMonetary | 30
loanClosingDate | 2026-05-01
requiredCompletionDate | 2027-05-01

## SOV
lineNumber | description | csiCode | scheduledValue | disciplineHint | zoneHint
001 | Site preparation and excavation | 02 30 00 | 32000 | ARCHITECTURE | site-wide
002 | Cast-in-place concrete foundations | 03 30 00 | 82000 | STRUCTURAL | foundation
003 | Slab on grade | 03 30 00 | 28000 | STRUCTURAL | main floor
004 | Rough carpentry / framing | 06 10 00 | 140000 | STRUCTURAL | main floor
005 | Roof sheathing and membrane | 07 50 00 | 42000 | ARCHITECTURE | roof
006 | Windows and exterior doors | 08 50 00 | 58000 | ARCHITECTURE | envelope
007 | Exterior cladding and trim | 07 46 00 | 62000 | ARCHITECTURE | envelope
008 | Insulation and air sealing (passive house) | 07 20 00 | 52000 | ARCHITECTURE | site-wide
009 | Rough plumbing | 22 11 00 | 38000 | PLUMBING | MEP chase
010 | Plumbing fixtures and trim | 22 40 00 | 24000 | PLUMBING | baths/kitchen
011 | Rough electrical | 26 05 00 | 44000 | ELECTRICAL | MEP chase
012 | Electrical fixtures and trim | 26 50 00 | 20000 | ELECTRICAL | site-wide
013 | HVAC — ERV and air-source heat pump | 23 00 00 | 58000 | ARCHITECTURE | mechanical room
014 | Interior gypsum drywall | 09 21 00 | 42000 | ARCHITECTURE | site-wide
015 | Interior finishes (paint, trim, flooring) | 09 90 00 | 62000 | ARCHITECTURE | site-wide
016 | Cabinets and countertops | 06 40 00 | 48000 | ARCHITECTURE | kitchen/baths
017 | Site work — driveway, walkways, grading | 32 10 00 | 28000 | ARCHITECTURE | site-wide
018 | Final cleanup and punch list | 01 74 00 | 8000 | ARCHITECTURE | site-wide
019 | Builder GC fee and overhead |  | 110000 | ARCHITECTURE
020 | Contingency |  | 72000 | ARCHITECTURE

## Milestones
sequence | name | plannedCompletionDate | plannedPercentOfLoan | status
1 | Site prep and foundation complete | 2026-06-30 | 12 | pending
2 | Rough framing and dried-in | 2026-08-15 | 28 | pending
3 | Exterior envelope closed | 2026-09-30 | 48 | pending
4 | Rough MEP inspections passed | 2026-11-15 | 62 | pending
5 | Insulation and drywall complete | 2026-12-31 | 75 | pending
6 | Interior finishes and fixtures | 2027-03-15 | 90 | pending
7 | Certificate of occupancy issued | 2027-04-15 | 98 | pending
8 | Final retainage release | 2027-05-01 | 100 | pending

## Milestone_Requirements
milestoneSequence | discipline | elementKindOrId | minPct | requiredDocs
1 | ARCHITECTURE | site_prep | 100 | building-department inspection record
1 | STRUCTURAL | foundation | 100 | concrete pour inspection sign-off
2 | STRUCTURAL | rough_framing | 100 | framing inspection sign-off
2 | ARCHITECTURE | roof_sheathing | 100 | roof inspection record
2 | ARCHITECTURE | windows | 90 | window schedule with installer invoice
3 | ARCHITECTURE | exterior_cladding | 95 | executed lien waiver from cladding sub
3 | ARCHITECTURE | windows | 100
3 | ARCHITECTURE | roof_sheathing | 100 | insurance COI current through 2027-05-31
4 | PLUMBING | rough_plumbing | 100 | plumbing rough inspection sign-off
4 | ELECTRICAL | rough_electrical | 100 | electrical rough inspection sign-off
4 | ARCHITECTURE | insulation_air_sealing | 60 | preliminary blower-door test report
5 | ARCHITECTURE | insulation_air_sealing | 100 | final blower-door test report
5 | ARCHITECTURE | drywall | 100 | drywall inspection sign-off
5 | ELECTRICAL | rough_electrical | 100
6 | ARCHITECTURE | cabinets | 95 | executed lien waiver from cabinet sub
6 | PLUMBING | plumbing_fixtures | 100 | plumbing fixture installation invoice
6 | ELECTRICAL | electrical_trim | 100
6 | ARCHITECTURE | final_finish | 85 | change-order log delta since last draw
7 | ARCHITECTURE | final_finish | 100 | Certificate of Occupancy issued by AHJ
7 | ARCHITECTURE | drywall | 100 | insurance COI current through 2027-06-30
8 | ARCHITECTURE | final_finish | 100 | final lien waivers from all subcontractors